## COVER_SHEET
Scenario Name |  | TEST_CASE
Scenario A
| Match | Per Well | Fixed | Initials | Date
Days to Build Pad | PAD |  | 14
Days Set Conductors | CONDUCTORS |  | 14
Days MOB In | MOB_IN |  | 3.5
Days Drill (ft/day or fixed) | DRILL | 1400
Days MOB Out | MOB_OUT |  | 3.5
Days to Log | LOG | 0.5
Days to Build Facilities | FAC |  | 49
Days to Frac | FRAC | 2.8
Days to First Sales after Frac | FLOWBACK | 30
Scenario B
|  | Per Well | Fixed | Initials | Date
Days to Build Pad | PAD |  | 14
Days Set Conductors | CONDUCTORS |  | 14
Days MOB In | MOB_IN |  | 3.5
Days Drill (ft/day or fixed) | DRILL | 1500
Days MOB Out | MOB_OUT |  | 3.5
Days to Log | LOG | 0.5
Days to Build Facilities | FAC |  | 45
Days to Frac | FRAC | 2
Days to First Sales after Frac | FLOWBACK | 20

## SCHEDULE
RIG | PAD | STYLE | RIG_START | PAD_START | PAD_END | CONDUCTORS | MOB_IN | DRILL | MOB_OUT | LOG | FAC | FRAC | FLOWBACK | DRILL_START | DRILL_END | COMPL_START | COMPL_END | PROD_START | PROD_END
DUC | PAD 01 | SCENARIO A | [13 empty] | 2019-03-15
RIG 01 | PAD 02 | SCENARIO B | 2019-01-01
RIG 01 | PAD 03 | SCENARIO A
RIG 01 | PAD 04 | SCENARIO B
RIG 01 | PAD 05 | SCENARIO A
RIG 02 | PAD 06 | SCENARIO B | 2019-04-01
RIG 02 | PAD 07 | SCENARIO A
RIG 02 | PAD 08 | SCENARIO B
RIG 02 | PAD 09 | SCENARIO A
RIG 02 | PAD 10 | SCENARIO B

## INPUTS
STYLE | UNIT | PAD | CONDUCTORS | MOB_IN | DRILL | MOB_OUT | LOG | FAC | FRAC | FLOWBACK | SCENARIO
SCENARIO A | PER_WELL | 0 | 0 | 0 | 1400 | 0 | 0.5 | 0 | 2.8 | 30 | TEST_CASE
SCENARIO A | FIXED | 14 | 14 | 3.5 | 0 | 3.5 | 0 | 49 | 0 | 0 | TEST_CASE
SCENARIO B | PER_WELL | 0 | 0 | 0 | 1500 | 0 | 0.5 | 0 | 2 | 20 | TEST_CASE
SCENARIO B | FIXED | 14 | 14 | 3.5 | 0 | 3.5 | 0 | 45 | 0 | 0 | TEST_CASE

## WELLS
PROPNUM | WELLNAME | AREA | PAD | DEPTH | DRILL_COST | COMPL_COST
A0001 | WELL A 1 | AREA 1 | PAD 01 | 10000 | 0 | 1000
A0002 | WELL A 2 | AREA 1 | PAD 01 | 10000 | 0 | 1000
A0003 | WELL A 3 | AREA 1 | PAD 01 | 10000 | 0 | 1000
A0004 | WELL A 4 | AREA 1 | PAD 01 | 10000 | 0 | 1000
A0005 | WELL B 1 | AREA 1 | PAD 02 | 10000 | 1000 | 1000
A0006 | WELL B 2 | AREA 1 | PAD 02 | 10000 | 1000 | 1000
A0007 | WELL B 3 | AREA 1 | PAD 02 | 10000 | 1000 | 1000
A0008 | WELL B 4 | AREA 1 | PAD 02 | 10000 | 1000 | 1000
A0009 | WELL C 1 | AREA 1 | PAD 03 | 10000 | 1000 | 1000
A0010 | WELL C 2 | AREA 1 | PAD 03 | 10000 | 1000 | 1000
A0011 | WELL C 3 | AREA 1 | PAD 03 | 10000 | 1000 | 1000
A0012 | WELL C 4 | AREA 1 | PAD 03 | 10000 | 1000 | 1000
A0013 | WELL D 1 | AREA 1 | PAD 04 | 10000 | 1000 | 1000
A0014 | WELL D 2 | AREA 1 | PAD 04 | 10000 | 1000 | 1000
A0015 | WELL D 3 | AREA 1 | PAD 04 | 10000 | 1000 | 1000
A0016 | WELL D 4 | AREA 1 | PAD 04 | 10000 | 1000 | 1000
A0017 | WELL E 1 | AREA 1 | PAD 05 | 10000 | 1000 | 1000
A0018 | WELL E 2 | AREA 1 | PAD 05 | 10000 | 1000 | 1000
A0019 | WELL E 3 | AREA 1 | PAD 05 | 10000 | 1000 | 1000
A0020 | WELL E 4 | AREA 1 | PAD 05 | 10000 | 1000 | 1000
A0021 | WELL F 1 | AREA 1 | PAD 06 | 10000 | 1000 | 1000
A0022 | WELL F 2 | AREA 1 | PAD 06 | 10000 | 1000 | 1000
A0023 | WELL F 3 | AREA 1 | PAD 06 | 10000 | 1000 | 1000
A0024 | WELL F 4 | AREA 1 | PAD 06 | 10000 | 1000 | 1000
A0025 | WELL G 1 | AREA 1 | PAD 07 | 10000 | 1000 | 1000
A0026 | WELL G 2 | AREA 1 | PAD 07 | 10000 | 1000 | 1000
A0027 | WELL G 3 | AREA 1 | PAD 07 | 10000 | 1000 | 1000
A0028 | WELL G 4 | AREA 1 | PAD 07 | 10000 | 1000 | 1000
A0029 | WELL H 1 | AREA 1 | PAD 08 | 10000 | 1000 | 1000
A0030 | WELL H 2 | AREA 1 | PAD 08 | 10000 | 1000 | 1000
A0031 | WELL H 3 | AREA 1 | PAD 08 | 10000 | 1000 | 1000
A0032 | WELL H 4 | AREA 1 | PAD 08 | 10000 | 1000 | 1000
A0033 | WELL I 1 | AREA 1 | PAD 09 | 10000 | 1000 | 1000
A0034 | WELL I 2 | AREA 1 | PAD 09 | 10000 | 1000 | 1000
A0035 | WELL I 3 | AREA 1 | PAD 09 | 10000 | 1000 | 1000
A0036 | WELL I 4 | AREA 1 | PAD 09 | 10000 | 1000 | 1000
A0037 | WELL J 1 | AREA 1 | PAD 10 | 10000 | 1000 | 1000
A0038 | WELL J 2 | AREA 1 | PAD 10 | 10000 | 1000 | 1000
A0039 | WELL J 3 | AREA 1 | PAD 10 | 10000 | 1000 | 1000
A0040 | WELL J 4 | AREA 1 | PAD 10 | 10000 | 1000 | 1000